## Sheet1
DAY-1: Monday Sprint Update
pr
Agenda for Monday | Team Members |  | Individual contribution | Goal for Tuesday | Documentation Status
Provided SRS Document- Case Study Discussion and Flow Planning | Anjali Patil | Diagrams | Class Diagram | Database and Stored Procedures | Documentation Done
| Snehal Barge |  | Use case Diagram
| Diksha Rambhad |  | ER Diagram
| Tanvi Dhasade |  | PPT
| Sanjana Mishra |  | DataBase Design
DAY-2: Tuesday Sprint Update
Agenda for Tuesday | Team Members | Controllers & Models | Individual contribution | Goal for Wenesday | Documentation Status
Employee Travel Booking System--Designing | Anjali Patil | Database and Stored Procedures | Employee | Window designing | Documentation Done
| Snehal Barge |  | Manager
| Diksha Rambhad |  | Travel Agent
| Tanvi Dhasade |  | Admin
| Sanjana Mishra |  | Admin
DAY-3: Wednesday Sprint Update
Agenda for Wednesdday | Team Members | Api Modification | Individual contribution | Goal for thursday | Documentation Status
Employee Travel Booking System- Functionalities | Anjali Patil | Window designing | Login pages, Employee main window | Business logic and Entities implementation | Documentation Done
| Snehal Barge |  | Manager window(approved/reject/history request)
| Diksha Rambhad |  | Travel agent window(approved/confirmed request)
| Tanvi Dhasade |  | Admin main window, Employee/Manager/Travel agent form
| Sanjana Mishra |  | Update/Delete/View Employee/Manager/Travel request
DAY-4: Thursay Sprint Update
Agenda for Thursdday | Team Members | Status | Individual contribution | Goal for Friday | Documentation Status
Employee Travel Booking System- Functionalities | Anjali Patil | Business logic and Entities implementation | Employee raising ticket functionality | Data access layer and Exception | Documentation done
| Snehal Barge |  | Functionality to approve/reject request
| Diksha Rambhad |  | Functionality to get approved request
| Tanvi Dhasade |  | Functionality to add/view Employee/Travel agent
| Sanjana Mishra |  | Functionality to update/delete Employee/Travel agent
DAY-5: Friday Sprint Update
Agenda for Friday | Team Members | Status | Individual contribution | Goal for Saturday | Documentation Status
Employee Travel Booking System- functionalities | Anjali Patil | Data access layer and Exception | Check status of raised request/ Cancel request | Integration | Documentation done
| Snehal Barge |  | Functionality to check history request
| Diksha Rambhad |  | Check ticket availability and confirm request
| Tanvi Dhasade |  | functionality to assign/change manager to employee
| Sanjana Mishra |  | functionality to view details of manager /employee
DAY-6: Saturday Sprint Update
Agenda for Friday | Team Members | Status | Individual contribution | Goal for Saturday | Documentation Status
Employee Travel Booking System | Anjali Patil | Integration |  | Testing and Debugging | Documentation done
Snehal Barge
Diksha Rambhad
Tanvi Dhasade
Sanjana Mishra
DAY-7: Monday Sprint Update
Agenda for Monday | Team Members | Status | Individual contribution | Product Explanation | Documentation Status
Employee Travel Booking System | Anjali Patil | Testing and Debugging |  | Product Explanation | Documentation done
Snehal Barge
Diksha Rambhad
Tanvi Dhasade
Sanjana Mishra